## SETTINGS
CAPACITY SETTINGS
Be honest here. A plan built on an optimistic week is not a plan.
YOUR WEEK
Weekly working hours | 40 | Hours you are at work, not hours you can sell
Target billable % | 75% | The share of working time that can be client work
WHAT COMES OUT OF IT
Admin hours per week | 4 | Invoicing, bookkeeping, email, filing
Sales hours per week | 2 | Proposals, enquiries, calls that are not billable
Recurring meetings per week | 1.5 | Standing calls you cannot move
Buffer % | 10% | For everything not on any list. Do not set it to zero.
PLANNING
Working days per week | 5
First week starting | 2026-09-21 | A Monday. Week 1 of the plan below.
Planning horizon (weeks) | 12
THE RESULT
Base billable capacity |  | Weekly hours × target billable %
Less recurring commitments |  | Base capacity − admin − sales − meetings
ADJUSTED WEEKLY CAPACITY |  | What is left after the buffer. This is the number the weekly plan is measured against.
Hours per working day |  | Adjusted capacity ÷ working days

## PROJECTS
PROJECTS
Estimated minus completed is what still has to fit somewhere.
Client | Project | Start date | Deadline | Estimated h | Completed h | Remaining h | Planned this week | Priority | Status
Northbeam Coffee Co. | Website redesign | 2026-09-07 | 2026-11-13 | 96 | 34 |  | 12 | High | Active
Harbourline Legal | Brand refresh | 2026-09-14 | 2026-10-16 | 40 | 12 |  | 8 | High | Active
Northbeam Coffee Co. | Marketing retainer | 2026-01-05 | 2026-12-31 | 300 | 210 |  | 6 | Medium | Retainer
Kestrel Software | Design system audit | 2026-10-05 | 2026-10-30 | 24 | 0 |  | 0 | Medium | Booked
Total remaining hours
Weeks of work at full capacity

## PLAN
WEEKLY PLAN
Committed hours are yours to type. Everything else is calculated.
Week | Starting | Available work h | Non-billable h | Adjusted capacity | Committed h | Free capacity | Utilisation | Overbooked h | Status
1 |  |  |  |  | 24
2 |  |  |  |  | 28
3 |  |  |  |  | 31
4 |  |  |  |  | 26
5 |  |  |  |  | 18
6 |  |  |  |  | 14
7 |  |  |  |  | 20
8 |  |  |  |  | 22
9 |  |  |  |  | 12
10 |  |  |  |  | 8
11 |  |  |  |  | 6
12 |  |  |  |  | 4
Totals over the horizon
AVAILABLE is under 80% utilised · BUSY is 80% to 100% · OVERBOOKED is over 100%, and means something has to move.

## PLANNER
NEW PROJECT PLANNER
Three inputs. Answer the “when can you start?” question with a date.
THE ENQUIRY
New project hours | 40 | Your estimate for the whole project
Desired hours per week | 10 | How hard you want to push it
Earliest start | 2026-09-21 | Not before this date
THE ANSWER
First feasible week |  | The first week on the plan that starts on or after your earliest start and has enough free capacity. 0 means no week in the horizon has room.
Starting |  | The Monday of that week
Estimated duration (weeks) |  | Project hours ÷ hours per week
Estimated completion |  | End of the last week of work
Free capacity in the horizon |  | Total unused capacity across every planned week
Does the project fit at all? |  | Ignoring pace: is there enough total room in the plan?
If the first feasible week is 0 but the project fits overall, the work can be done — just not at the pace you asked for. Lower the desired hours per week and look again.