CHANGE REQUEST

{{CHANGE_REQUEST_NUMBER}} · {{PROJECT_NAME}}

| Project | {{PROJECT_NAME}} |
| --- | --- |
| Client | {{CLIENT_NAME}} |
| Original scope reference | {{SOW_REFERENCE}}, dated {{SOW_DATE}} |
| Request date | {{REQUEST_DATE}} |
| Requested by | {{REQUESTED_BY}} |
| Prepared by | {{FREELANCER_NAME}} |

Impact summary

| Impact | Change |
| --- | --- |
| Additional effort | +12 hours |
| Additional cost | +$900.00 |
| Schedule impact | +4 working days |
| Current target date | 20 October |
| Revised target date | 24 October |
| Status | Awaiting approval |

No work on this change begins until the decision below is signed. The figures above assume approval by {{DECISION_BY_DATE}}; after that date the schedule impact may increase.

What is being requested

{{CHANGE_DESCRIPTION}}

Why

{{CHANGE_REASON}}

Original requirement versus new requirement

| Item | Originally agreed | Now requested |
| --- | --- | --- |
| Product page templates | Three templates | Four templates |
| Revision rounds | Two per deliverable | Two per deliverable (unchanged) |
| {{ITEM_3}} | {{ORIGINAL_3}} | {{REQUESTED_3}} |

Deliverables affected

•  {{AFFECTED_DELIVERABLE_1}}

•  {{AFFECTED_DELIVERABLE_2}}

Additional effort and cost

| Activity | Hours | Rate | Cost |
| --- | --- | --- | --- |
| Design of the additional template | 6.0 | $75.00 | $450.00 |
| Build and responsive testing | 4.5 | $75.00 | $337.50 |
| Revision round and review | 1.5 | $75.00 | $112.50 |
| Total additional cost | 12.0 |  | $900.00 |

Timeline impact

| Working days added | 4 |
| --- | --- |
| Milestones affected | {{AFFECTED_MILESTONES}} |
| Current target date | {{CURRENT_TARGET_DATE}} |
| Revised target date | {{REVISED_TARGET_DATE}} |

The schedule impact is longer than the hours alone because the additional work has to fit around commitments already scheduled. Twelve hours of work is not twelve hours of calendar.

Dependencies and risks

•  Content for the additional template is supplied by {{CONTENT_DATE}}.

•  {{DEPENDENCY_2}}

•  Risk: {{RISK_1}}

Decision

Please mark one option, sign and return.

☐  Approved — proceed as described above

☐  Approved with changes — see notes below

☐  Declined — the project continues as originally scoped

☐  Deferred — revisit on {{DEFER_DATE}}

Notes: {{DECISION_NOTES}}

Approval

| Approved for {{CLIENT_NAME}} Signature Name Date | For {{FREELANCER_BUSINESS}} Signature Name Date |
| --- | --- |

Once signed, attach this to the scope of work. The revised dates and total replace the ones in the original document.