## PROJECT
PROJECT SETUP
Use the value the project ended at, not the value you quoted.
THE PROJECT
Client | Northbeam Coffee Co.
Project | Website redesign — Phase 1
Pricing type | Fixed price
Start date | 2026-07-06
Completion date | 2026-09-11
VALUE
Original project value | 4800 | What was quoted and accepted
Approved changes | 900 | Total of approved change requests
Discounts given | 200 | Goodwill reductions, late-delivery credits
Expenses reimbursed | 320 | Costs recharged to the client at cost
TARGETS
Target hourly rate | 90 | What you intended to earn per hour
Internal cost rate | 0 | OPTIONAL. Leave at 0 unless you cost your own time or subcontract.
Internal cost rate is optional on purpose. A sole trader has no meaningful internal cost, and inventing one produces a margin figure that means nothing. Left at zero, the margin rows on OUTPUTS simply read as not applicable.

## TIME
TIME RECORDS
Log the unpaid hours too — they are the ones that explain the rate.
Date | Activity | Category | Hours | Billable? | Notes
2026-07-06 | Kickoff and discovery workshop | Meeting | 3 | Yes
2026-07-08 | Content audit | Research | 4 | Yes
2026-07-13 | Wireframes, all templates | Delivery | 11 | Yes
2026-07-20 | Visual design, homepage | Delivery | 9 | Yes
2026-07-27 | Visual design, product pages | Delivery | 8.5 | Yes
2026-08-03 | Revision round 1 | Revision | 5 | Yes | Within allowance
2026-08-07 | Revision round 2 | Revision | 4 | Yes | Within allowance
2026-08-11 | Revision round 3 | Revision | 2 | No | Beyond allowance, absorbed
2026-08-14 | Weekly check-in calls (4) | Meeting | 3 | No | Not quoted for
2026-08-18 | Build, homepage and templates | Delivery | 12 | Yes
2026-08-25 | Content loading | Delivery | 4 | Yes | Client-supplied copy
2026-09-01 | Cross-browser fixes | Delivery | 3 | Yes
2026-09-03 | Scope discussion for extra template | Sales / scope | 1.5 | No | Became change request CR-01
2026-09-08 | Handover documentation and call | Communication | 2.5 | No | Not quoted for
2026-09-11 | Invoicing and project filing | Admin | 1 | No
Total hours
Billable hours
Delivery hours

## COSTS
PROJECT COSTS
The payment fee is the one everybody forgets.
DIRECT COSTS
Contractors | 0 | Anyone you paid to do part of the work
Software bought for this project | 180 | Licences you would not otherwise have bought
Travel | 64
Materials | 76 | Stock media, print, physical goods
Other expenses | 0
Direct costs
PAYMENT FEES
Processing fee % | 2.9% | Card, platform or marketplace percentage
Fixed fees | 1.2 | Per-transaction and transfer charges
Reimbursed expenses are entered on the PROJECT sheet as value and here as cost, so they net to zero rather than inflating the project.

## OUTPUTS
PROJECT PROFITABILITY
VALUE
Original project value
Approved change value
Discounts given
CURRENT CONTRACT VALUE |  | Original + approved changes − discounts
Expenses reimbursed |  | Recharged at cost; cancels out below
HOURS
Total project hours
Delivery hours |  | Hours categorised as Delivery
Non-delivery hours |  | Meetings, revisions, admin, research, communication, scope
Billable hours
Unpaid work % |  | Hours nobody paid for, as a share of every hour worked
COSTS AND REVENUE
Direct costs
Payment fees |  | Percentage of everything invoiced, plus the fixed charges
Total expenses
NET PROJECT REVENUE |  | Contract value + reimbursed expenses − total expenses
THE RATE
EFFECTIVE HOURLY RATE |  | Net revenue ÷ every hour the project took
Target hourly rate
Rate variance |  | Negative means the project paid less per hour than you intended
Gross project margin |  | Before any cost for your own time
OPTIONAL: INTERNAL LABOUR COST
Internal cost rate |  | Set on the PROJECT sheet. Zero means not applicable.
Labour cost
Project profit |  | Net revenue − labour cost, when a cost rate is supplied
Project margin %
WHERE THE TIME WENT
Category | Hours | Share of project
Delivery
Meeting
Revision
Admin
Research
Communication
Sales / scope
Read this next to the rate variance. When the effective rate is below target, the categories above name the reason — and revisions and meetings are the usual answer.